LOAGMA CMS

Reports Module — Full Implementation Plan

Telecaller + Admin, both sides  ·  Prepared 16 September 2026

## 1. Objective & guiding principle

Build a complete Reports module so that every telecaller can see their own activity in real time, and Admin can see the same data rolled up across the whole team, with the ability to drill into any individual. Rather than building 11 Telecaller screens and 11 separate Admin screens (22 builds), each report is one underlying screen with role-scoped data: a telecaller sees only their own record, Admin sees everyone with a person/date filter — this is the same pattern already used successfully in the existing Team Report and Team Call History screens.

The single biggest finding from the audit: most of these reports cannot be built as "just a screen" — the underlying data isn't captured yet (e.g. no call outcome, no lead source, no follow-up tracking). So this plan starts with the data model, not the UI.

## 2. Foundational data model changes (build first)

These changes touch the Call and Lead records and add two new entities. Nothing in Phase 1 onward can be "proper" without this — it's the prerequisite for 9 of the 11 reports.

| Entity | New field(s) / model | What it captures | Unlocks report(s) |
| --- | --- | --- | --- |
| Call | outcome (enum) | Interested / Not Interested / Converted / Callback Requested / No Answer / Busy / Wrong Number / Not Reachable | Call Outcome, Conversion, Lost Leads, Performance |
| Call | notes (text) | Free-text note the telecaller adds after a call | Daily Call Report, Performance |
| Lead | source (enum) | Referral / Campaign / Walk-in / Cold Call / Website / Other | Lead Source, Campaign Performance |
| Lead | status (enum) | New / In Progress / Interested / Converted / Lost | Conversion Report, Lost Leads, Performance |
| Lead | lost_reason (enum, nullable) | Price / Not Interested / Competitor / Unreachable / Other | Lost Leads |
| Follow-up (new entity) | lead_id, telecaller_id, due_date, type (Follow-up/Callback), status, notes, created_from_call_id | New table to track promised next actions | Follow-up Report, Callback Report |
| Campaign (new entity) | name, channel, start_date, end_date, budget (optional), status | New table; leads link to a campaign_id | Campaign Performance, Lead Source |
| Target (extend existing) | telecaller_id, period, call_target, conversion_target | Existing "Target" tile needs telecaller-level, period-based targets, not just a flag | Telecaller Performance |

## 3. Full report specification — what each screen shows

### 3a. Telecaller view vs. Admin view

| Report | Telecaller view (sees own data only) | Admin view (sees all + drill-down) |
| --- | --- | --- |
| Call Outcome | Dropdown shown right after ending a call; "my outcomes today/this week" chart | Team-wide outcome breakdown; drill into any telecaller; spot who isn't logging outcomes |
| Daily Call Report | My calls today/any date — list with time, number, outcome, duration | Same, any telecaller, any date; daily total across team |
| Call Duration | My total & average talk time, trend line | Team total/average, per-telecaller comparison |
| Productivity | My daily/weekly activity: calls + visits + attendance in one view | Polish of existing Team Report tiles; per-telecaller trend |
| Follow-up Report | My pending / overdue / done follow-ups, with due-date reminders | Team follow-up compliance; overdue alerts per telecaller |
| Callback Report | My upcoming & missed callbacks | Team callback adherence rate |
| Lost Leads | My lost leads with reasons, so I can revisit them | Team lost-lead rate, top reasons, recovery candidates |
| Telecaller Performance | My scorecard vs. my target this period | Leaderboard/ranking across all telecallers |
| Conversion Report | My conversion count & rate this period | Team conversion rate; funnel: leads → contacted → interested → converted |
| Lead Source | Sources of leads assigned to me | Source breakdown + conversion rate by source, across team |
| Campaign Performance | Leads I've worked from each campaign (secondary view) | Leads generated, conversion %, cost/lead per campaign |

### 3b. Metrics, filters, dependencies & priority

| Report | Key metrics | Filters | Data dependency | Priority |
| --- | --- | --- | --- | --- |
| Call Outcome | Count & % per outcome type | Date range, telecaller, outcome | Call.outcome | High |
| Daily Call Report | Calls made, answered, per-hour timeline | Date, telecaller | Call.outcome, Call.duration | High |
| Call Duration | Total, average, longest/shortest call | Date range, telecaller | Call.duration (exists) | Medium |
| Productivity | Calls, visits, attendance, active hours | Date range, telecaller | Mostly exists | Medium |
| Follow-up Report | Pending, overdue, completed, compliance % | Date, status, telecaller | New Follow-up entity | High |
| Callback Report | Scheduled, on-time, missed | Date, status, telecaller | Follow-up entity (type=Callback) | Med-High |
| Lost Leads | Lost count, lost rate %, reasons breakdown | Date, reason, telecaller | Lead.status, Lead.lost_reason | Medium |
| Telecaller Performance | Calls, answer %, conversions, target achievement % | Period, sort by metric | Target entity, Call Outcome, Conversion | High |
| Conversion Report | Conversions, conversion rate %, avg calls-to-convert | Date range, telecaller, source | Lead.status linked to Call | High |
| Lead Source | Lead count & conversion % by source | Date range, source | Lead.source | Medium |
| Campaign Performance | Leads, conversion %, cost per lead | Campaign, date range | New Campaign entity + linked leads | Medium |

## 4. Phased roadmap

Total estimated build time: 11.5–16 weeks for one developer working sequentially; shorter if Phase 1 and the data-model work in Phase 0 are done by the same person in parallel with a second developer starting UI work early on reports that don't need new entities (Call Duration, Productivity).

| Phase | Focus | Duration | What ships |
| --- | --- | --- | --- |
| Phase 0 | Data Foundation | 1.5–2 weeks | Add outcome/source/status fields, build Follow-up entity, extend Target entity. No new report screens yet — this is plumbing every later phase depends on. Includes: Call.outcome, Call.notes, Lead.source, Lead.status, Lead.lost_reason, Follow-up entity, Target extension. |
| Phase 1 | Core Daily Reports | 2–3 weeks | Ship the reports that only need Phase 0 fields plus UI. Immediate value, low risk. Includes: Call Outcome, Daily Call Report, Call Duration, Productivity (both Telecaller + Admin views). |
| Phase 2 | Follow-Through & Funnel Hygiene | 3–4 weeks | Close the loop on leads so nothing falls through the cracks. Includes: Follow-up Report, Callback Report, Lost Leads (both Telecaller + Admin views). |
| Phase 3 | Performance & Growth | 3–4 weeks | Heavier reports that aggregate Phase 0–2 data into scorecards and funnels. Includes: Telecaller Performance (leaderboard), Conversion Report, Lead Source. |
| Phase 4 | Campaign Layer | 2–3 weeks | Only worth building once campaigns are actually run in a structured way — build the Campaign entity + management screen first, then the report. Includes: Campaign entity + admin management UI, Campaign Performance report. |

## 5. Cross-cutting requirements (apply to every report)

- Date filter on every report: Today / Yesterday / Last 7 days / Last 30 days / Custom range — reuse the exact pattern already built into Team Report's filter sheet.

- Role scoping: Telecaller auth token restricts queries to their own telecaller_id server-side (not just hidden in the UI) — this is a security requirement, not a display preference.

- Admin drill-down: every team-wide number should be tappable to jump to that telecaller's own version of the report, same as Team Call History already does.

- Export: Admin should be able to export any report to CSV/PDF for sharing with management — not needed on the Telecaller side.

- Empty & loading states: match the existing style already seen in Team Report ("No calls in this period").

- Refresh: pull-to-refresh + the existing refresh icon pattern, kept consistent across all new screens.

## 6. Admin-only additions needed

The proposed menu includes a Settings section (Call Outcomes, Lead Sources, Campaigns, Follow-up Types) that does not exist in the live app today. This is required infrastructure, not optional — it's where Admin defines the dropdown values that power Call Outcome, Lead Source, Campaign Performance and Follow-up Report. Build this alongside Phase 0.

- Settings > Call Outcomes — manage the list of outcome options telecallers choose from after each call.

- Settings > Lead Sources — manage source options (Referral, Campaign, Walk-in, etc.).

- Settings > Campaigns — create/edit campaigns (name, channel, dates, budget) — needed before Phase 4.

- Settings > Follow-up Types — manage follow-up/callback type options.

## 7. Telecaller-only additions needed

These aren't reports, but the reports are meaningless without them — a telecaller needs a way to generate the data in the first place.

- Telecaller Dashboard — a home screen for the telecaller role itself (this audit only had Admin login; confirm whether this already exists).

- Leads > All Leads / Assigned Leads — the telecaller's working list of leads to call.

- Leads > Follow-ups — the action list that feeds the Follow-up Report.

- Calls > Make Call — the call screen itself must capture outcome + notes at the end of every call; this single interaction is what makes 9 of the 11 reports possible.

- Calls > Call History / Call Recording — telecaller's own version of what Admin already sees in Team Call History.

## 8. Effort summary (at a glance)

| Report | Phase | Priority | Effort | Status today |
| --- | --- | --- | --- | --- |
| Call Outcome | Phase 1 | High | S | Not built |
| Daily Call Report | Phase 1 | High | S | Partial |
| Call Duration | Phase 1 | Medium | S | Exists |
| Productivity | Phase 1 | Medium | S | Partial |
| Follow-up Report | Phase 2 | High | M | Not built |
| Callback Report | Phase 2 | Med-High | S | Not built |
| Lost Leads | Phase 2 | Medium | S | Not built |
| Telecaller Performance | Phase 3 | High | L | Partial |
| Conversion Report | Phase 3 | High | L | Not built |
| Lead Source | Phase 3 | Medium | S/M | Not built |
| Campaign Performance | Phase 4 | Medium | L | Not built |

Effort key: S = small (days, mostly UI on top of existing/simple data), M = medium (new entity or moderate backend logic), L = large (new entity + aggregation/funnel logic across multiple sources).

## 9. Risks & open questions

- Telecaller-side login was not available during the audit — confirm whether a Telecaller Dashboard, Leads, and Calls section already exist there before rebuilding them. This plan assumes they need to be built; they may partially exist.

- Confirm the calling mechanism: is calling done through an in-app dialer/VoIP integration (which can auto-capture duration and recording), or are telecallers dialing externally and logging manually? This materially changes the effort for Call Duration, Call Recording, and how reliably Call Outcome gets captured.

- Confirm backend/tech stack ownership — this plan was scoped from the live front end only (Flutter web app); actual effort depends on the backend framework and database already in use.

- Decide whether Campaigns (Phase 4) are worth building now — if no structured marketing campaigns are run yet, defer this phase entirely rather than building a report with no data to show.

- Decide on data retention/history — how far back reports need to look (affects whether raw call/lead history needs backfilling or reports only work going forward).

## 10. Recommended next steps

- Confirm/adjust the phase order and priorities in this plan (Section 4).

- Get Telecaller-role login credentials so the existing Telecaller-side app can be audited the same way Admin was — this may shrink the plan significantly if some pieces already exist.

- Answer the open questions in Section 9, especially the dialer/VoIP question — it's the single biggest swing factor on effort.

- Once confirmed, this plan can be converted into a developer-ready ticket list (one ticket per row in Section 3b), split by phase.

Prepared from a live audit of the Admin side of loagma-crm-web.onrender.com. Telecaller-side details are planning assumptions pending confirmation (see Section 9).